## Sheet1
ICJO Coordinator Check List
Month | To Do | Started | Completed | Notes
Oct
DMAIC: Start: State Workflows
DMAIC: Start: Policy & Procedure Document(s)
DMAIC: Start: State Communication Structure & Plan
DMAIC: Start: State Learning Plan
Develop peer-to-peer state relationships
Complete UNITY State Zone Structure
Wed @ 1's
Nov
DMAIC: Complete: State Workflows
DMAIC: Complete: Policy & Procedure Document(s)
DMAIC: Complete: State Communication Structure & Plan
DMAIC: Complete: State Learning Plan
DMAIC: Start: Improve of DMAIC List
DMAIC: Start: JIDS Cases
Develop peer-to-peer state relationships
Develop 60 Second UNITY Talk: Reason for Change & Benefits
Solicit Field Officer Transition & UNITY Questions
Identify JIDS case review & migration team members
IT Technology Letter w/ SmartSheet Online Question Form
Review Learner Progress
Wed @ 1's Peer-to-Peer
Wed @ 1's Peer-to-Peer
Wed @ 1's Peer-to-Peer
Dec
DMAIC: Complete: Improve of DMAIC List
DMAIC: Complete: JIDS Cases
Finalize peer-to-peer state relationships
Finalize JIDS case review & migration team members
Finalize 60 Second UNITY Talk: Reason for Change & Benefits
Solicit Field Officer Transition & UNITY Questions
Wed @ 1's Peer-to-Peer
Wed @ 1's Peer-to-Peer
Wed @ 1's Peer-to-Peer
Review Learner Progress
JIDS Data Active Case Review
Finalize January Communication Plans
Jan
Finalize JIDS Case review support team
Finalize UNITY Data Migration Review support team
Solicit Field Officer Transition & UNITY Questions
Wed @ 1's Peer-to-Peer
Wed @ 1's Peer-to-Peer
Pre-Golive preparedness WebEx
Wed @ 1's Peer-to-Peer
Wed @ 1's Peer-to-Peer
Pre-Golive preparedness WebEx
Review Learner Progress
JIDS Data Active Case Review
Case Managers ID Cases that will drop off in Feb
Communicate Feb go-live plan & process to state personnel
Excel template for tracking open migration cases
Feb
Communicate Feb go-live plan & process to state personnel
Wed @ 1's Peer-to-Peer
Wed @ 1's Peer-to-Peer
Go-Live Day / Date /
UNITY Migration Data & Case Review
Wed @ 1's Peer-to-Peer
Mar
Wed @ 1's Peer-to-Peer
Wed @ 1's Peer-to-Peer